## Simple Business Risk Register
SIMPLE BUSINESS RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
EXAMPLE: CSS library doesn't support modals | Key design feature will be unavailable on login screen | 4 | 2 | 8 | Check documentation before chosing CSS library | Front-end team | 1
Client may pivot to a mobile-first design | Aspects of the application will be unusable on small screens | 5 | 3 | 15 | Regular meetings with client to demonstrate prototypes and get feedback | Product Owner | 2
Refactoring late in the project (e.g. changing libaries or API endpoints) | Refactoring huge or specified amount of code increasing workload | 3 | 2 | 6 | Spend adequate time researching libraries/APIs prior to implementation | All Tech-Team | 3
Up to date code base | If members aren't up to date with the github repo, then merging will lead to conflicts. Thus slowing the development process | 2 | 3 | 6 | Frequent pull & merges and make commits to feature branches | All Tech-Team | 4
Google Maps crashing or server maintenance | Main application functionality will not work | 3 | 2 | 5 | Regularly test the google maps API and be aware of when the website is down for maintenance | Front-end team | 5
Limited accessibillity | Application will be harder to scale as it wont be practical for particular demographics | 2 | 3 | 8 | Research into UX/UI to improve experience for multiple demographics | Front-end team
Security vulnerablities | During developement or production, foreign parties could gain access to user information | 5 | 2 | 10 | Put measures in place to prevent data leaks, and manage access to the database. Adhere to GDPR regulations. | Product Owner & Front-end team
API Integration bottleneck | Implementing the API could cause a development bottleneck, due to its learning curve or documentation quality | 2 | 3 | 6 | Have a section of the team responsible for learning the API documentation so not all team resources are used up at once | Front-end team
Changes in project scope | The final product wont be in line with the client specification | 4 | 2 | 8 | Regular meetings with client to demonstrate prototypes and get feedback | Product Owner

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.